## Scales
SeatMe — Risk Scales (custom, not 0–1 and not dollars)
Probability scale
Level | Label | Meaning
1 | Rare | Very unlikely during the project / a typical event
2 | Unlikely | Could happen but not expected
3 | Possible | Might happen at some point
4 | Likely | Expected to happen sometimes
5 | Almost certain | Expected to happen most of the time
Cost / impact scale
Level | Label | Meaning
1 | Negligible | Cosmetic / no real effect
2 | Minor | Small inconvenience, easy workaround
3 | Moderate | Noticeable disruption, some rework
4 | Major | Significant outage / data or trust impact
5 | Severe | Project- or security-critical failure
Exposure = Probability × Cost (range 1–25)
Band | Exposure range
Low | 1–5
Medium | 6–12
High | 13–19
Critical | 20–25

## Risk Register
ID | Category | Risk | Probability (1-5) | Cost (1-5) | Exposure (P×C) | Band | Mitigation
R01 | Operational | AWS Academy lab session expires / is reset, wiping all resources | 4 | 4 | 16 | High | One-command redeploy (redeploy_all.py); keep all infra as code; export DynamoDB data before stopping the lab.
R02 | Security | API Gateway has no gateway-level JWT authorizer; auth is enforced in-Lambda instead | 3 | 5 | 15 | High | Write endpoints and the admin route validate the Cognito token + ownership/group in-Lambda (_common.require_owner); public reads stay open for RSVP. Roadmap: add a Cognito JWT authorizer to the HTTP API.
R03 | Security | Weak/known seeded admin password or leaked admin credentials | 3 | 5 | 15 | High | Force password change on first use; override via SEATME_ADMIN_PASSWORD; keep the admin group small.
R04 | Delivery | SNS subscription confirmation friction -> invitations not delivered | 4 | 3 | 12 | Medium | Clear UI copy explaining the one-time confirm email; report pending vs sent counts; resend support.
R05 | Delivery | SES blocked in lab -> verification emails land in spam / not delivered | 4 | 3 | 12 | Medium | Graceful fallback to Cognito built-in mailer; document spam-folder check; resend-code action.
R07 | Data | Accidental teardown / no backups -> permanent data loss | 3 | 4 | 12 | Medium | Confirmation prompts on destructive commands; enable DynamoDB PITR / on-demand backups before teardown.
R10 | Reliability | Lambda code regression breaks the API during a redeploy | 3 | 3 | 9 | Medium | Idempotent deploys; validate with the OpenAPI spec; roadmap: staged alias + automated smoke tests.
R12 | Privacy | No-login preview link (?host=) lets anyone with the link view an event's details (read-only) | 3 | 3 | 9 | Medium | Editing now requires login (writes authorized in-Lambda), so the link is view-only; treat it as a shareable secret. Roadmap: signed, expiring preview tokens instead of raw email.
R06 | Availability | Single-region (us-east-1) outage takes the whole app down | 2 | 4 | 8 | Medium | Accept for MVP; roadmap: multi-region S3 + DynamoDB global tables + Route 53 failover.
R08 | Scalability | DynamoDB 400 KB item limit exceeded for very large events | 2 | 4 | 8 | Medium | Monitor item size; roadmap: split guests into child items keyed by host+guest for big events.
R09 | Security | XSS via guest-supplied fields (name, song request) | 2 | 4 | 8 | Medium | Frontend escapes all user input with escapeHtml() before DOM insertion; server-side validation.
R13 | Config | Placeholder injection fails -> site can't reach API / Cognito | 2 | 4 | 8 | Medium | deploy_frontend.py injects config at upload; 'redeploy to re-inject' documented in troubleshooting.
R11 | Cost | Cost overrun from traffic spikes or abuse of open endpoints | 2 | 3 | 6 | Medium | Pay-per-use scales with usage; roadmap: API throttling/usage plans and AWS Budgets alerts.

## Top Risk Mitigation
Biggest risk — mitigation plan
Risk ID | R01
Category | Operational
Risk | AWS Academy lab session expires / is reset, wiping all resources
Probability | 4/5
Cost / impact | 4/5
Exposure | 16 (High)
Why it is the biggest risk
The project runs in an AWS Academy lab whose session/credentials expire and whose 'Reset' wipes every resource. If that happens during grading the live link and data disappear, which is both Likely (4) and Major (4).
Mitigation plan
1. Infrastructure as code: the entire stack redeploys with `python redeploy_all.py` in minutes, so a wiped environment is fully recoverable.
2. Data export: before stopping the lab, export the DynamoDB `SeatMe` table (or enable point-in-time recovery / on-demand backup) so event data can be restored.
3. Avoid the lab 'Reset' button; only stop/start the lab to preserve resources.
4. Keep the redeploy idempotent so re-running updates resources in place without manual cleanup.
5. Document the seeded credentials and demo link so the app can be re-verified immediately after a redeploy.
6. Roadmap: move to a standard AWS account (no lab expiry) and add DynamoDB global tables + multi-region S3 for durability.
Runner-up risks to watch
R02 (15, High): API Gateway has no gateway-level JWT authorizer; auth is enforced in-Lambda instead — Write endpoints and the admin route validate the Cognito token + ownership/group in-Lambda (_common.require_owner); public reads stay open for RSVP. Roadmap: add a Cognito JWT authorizer to the HTTP API.
R03 (15, High): Weak/known seeded admin password or leaked admin credentials — Force password change on first use; override via SEATME_ADMIN_PASSWORD; keep the admin group small.